Plan for Chuanshun Wei’s dissertation (11/04/2025)

1. Tittle:  Searching for DM and Measurement of ZZ Production Differential Cross-section with ll + MET Final State at √S = 13 TeV with ATLAS Detector

2. Thesis content

Abstract in both English and Chinese

Chapter 1 Introduction

Chapter 2 SM and di-boson physics, DM

Chapter 3 The ATLAS detector at LHC

Chapter 4 DM search with ll + MET Final State

Chapter 5 ZZ Cross-section measurement

Chapter 6 Upgrade of Muon Spectrum of the ATLAS detector

Chapter 7 Prospect and Summary

Bibliography

Acknowledgement

3. Deadlines (X= defense date)

(Submit thesis before June, avoid the summer break)

[Ask Juan about the thesis submission schedule and regulation]

Deadline for submitting dissertation to supervisors: //2026

Deadline for submitting dissertation to ENPP:   //2026

Deadline for submitting dissertation to USTC graduate school:  (01/15/2026)(Considering the late New Year in 2026, could be postponed by ~ 2 weeks)

Slides of 40 minutes presentation: /

Rehearse:  before /

Date of thesis defense: //2026

4. Thesis reviewers

USTC:  Yang Li, Yusheng Wu/Lailin, Ziping Zhang

SJTU:   Haijun Yang

SDU:    Haifeng Li

PKU:    Qiang Li

5. Defense committee members

USTC:  Yang Li, Yusheng Wu/Lailin, Ziping Zhang

SJTU:   Haijun Yang

SDU:    Haifeng Li

PKU:    Qiang Li

Secretary:   (???)

Supervisors: Bing Zhou,  Zhengguo Zhao

Detailed Plan:

Chapter 1: Introduction (Completed)

1.1 Particle Physics

1.2 Analyses

1.2.1 Measurement of ZZ Production

1.2.2 Search for Dark Matter with 𝑙𝑙 + MET Final State

1.3 Hardware Work

Chapter 2: The Standard Model of Particle Physics ()

2.1 Standard Model (Almost done.)

2.1.1 Fundamental Particles

2.1.2 Fundamental Forces

2.1.3 Math Theory Framework

2.1.4 Di-boson Production

2.2 Beyond the Standard Model and Dark Matter Search (3-4 days, after all other chapters)

2.2.1 BSM Theory (1 day)

2.3 Higgs-related mechanism/theory (2-3 days, after all other chapters)

Chapter 3: The LHC and ATLAS Experiment (Completed)

3.1 The Large Hadron Collider

3.1.1 High-Luminosity LHC Upgrade

3.1.2 Collider Physics

3.2 The ATLAS Detector

3.2.1 Inner Tracker

3.2.2 Calorimetry

3.2.3 Muon Spectrometer

3.2.4 Magnet System

Chapter 4: Measurement of ZZ Production with 𝑙𝑙𝜈𝜈 Final State(10 days, 11/14)

(Yusheng, WZ; Lailin, ZZ; Lishu, WW)

4.0 Di-boson Physics(ZZ)

4.1 Data and Monte Carlo Samples

4.2 Event Selection

4.2.1 Objects

4.2.2 Pre-selection

4.2.3 Selection in Reco and Truth Level

4.3 Background Estimation

4.3.1 3l

4.3.2 𝑒𝜇

4.3.3 Z+jet

4.3.4 Others

4.4 Systematic Uncertainty

4.5 Unfolding

4.6 DNN Optimization

4.7 Results

Chapter 5: Search for Dark Matter with 𝑙𝑙 + MET Final State (14 days, 11/28)

5.1 Event Selection (2 days)

5.2 Background Estimation (3 days)

5.3 Systematic Uncertainty (3 day)

5.4 Results (2 days)

Chapter 6: Construction of sMDT Chambers for the upgrade of Muon Spectrum on the ATLAS Detector (10 days, 12/08)

6.1 sMDT tube construction (3 days)

6.1.1 sMDT tube Assembly (1 days)

6.1.2 sMDT tube Quality Test (2 days)

6.2 sMDT Chamber Construction (3 days)

6.2.1 Chamber Assembly (1 days)

6.2.2 Chamber Quality Test (2 days)

Chapter 7: Prospect and Summary (2-3 days, finish before 12/11)

Appendix, Acknowledgements, and Publications (finalize before 12/14)

A.1 Appendix (1 day)

Acknowledgements and Publications (1 day)

Revision and Finalization (Dec. 2025)